## Manual Test Cases
Test Case ID | Module | Source Artifact | Requirement or Action | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Test Type | Automation Reference | Notes
TC-AUTH-001 | Authentication | Areas/Identity/Pages/Account/Register.cshtml | Register a new user account | Application is running; test email is not already registered. | Open Register page; enter email, password, confirm password, and required profile data; submit the form. | Email qa.user1@example.com; valid password Test123! | New user account is created and the user can proceed according to Identity flow. | Pending manual execution | Not Run | High | Manual Functional | No custom automated coverage | Identity UI exists in project but is not covered by the custom xUnit suite.
TC-AUTH-002 | Authentication | Areas/Identity/Pages/Account/Login.cshtml | Login with valid credentials | A valid user account exists. | Open Login page; enter valid credentials; submit the form. | Email qa.user1@example.com; password Test123! | User is authenticated and navigation reflects logged-in state. | Pending manual execution | Not Run | High | Manual Functional | No custom automated coverage | Program.cs configures AddDefaultIdentity.
TC-AUTH-003 | Authentication | Areas/Identity/Pages/Account/Login.cshtml | Reject invalid login | A valid user account exists. | Open Login page; enter valid email with incorrect password; submit the form. | Email qa.user1@example.com; password Wrong123! | Login is rejected and the user remains unauthenticated. | Pending manual execution | Not Run | High | Negative Manual | No custom automated coverage | Checks Identity validation behavior.
TC-AUTH-004 | Authentication | Areas/Identity/Pages/Account/Logout.cshtml | Logout authenticated user | User is logged in. | Use the Logout action; then open a user-only page such as /Orders/MyOrders. | Existing authenticated user | User session ends and protected pages require authentication. | Pending manual execution | Not Run | Medium | Manual Functional | No custom automated coverage | OrdersController has Authorize role protection.
TC-HOME-001 | Home | Controllers/HomeController.cs; Views/Shared/_Layout.cshtml | Open default home route | Application is running. | Open the root URL configured by launchSettings; observe page load and navigation. | http://localhost:5162 or https://localhost:7114 | Home page loads without server error and shared layout is visible. | Pending manual execution | Not Run | Medium | Smoke Manual | No custom automated coverage | HomeController exposes Index action.
TC-DISH-001 | Dish Menu | Controllers/DishController.cs; Views/Dish/Index.cshtml | Display dish list | Application has database data or seeded dishes. | Open /Dish/Index or menu route; inspect listed dishes. | Existing dish records | Dish list is displayed with user-readable information and no layout break. | Pending manual execution | Not Run | High | Manual Functional | DishControllerTests.Index_ReturnsViewWithDishes; DishServiceTests.GetAllAsync_ReturnsAllDishes | Automated tests cover controller/service result, not browser rendering.
TC-DISH-002 | Dish Menu | Controllers/DishController.cs; Views/Dish/Details.cshtml | Display dish details | At least one dish exists. | Open details page for an existing dish id; review description, category, ingredients, allergens, and nutrition sections. | Existing dish id | Details page shows the selected dish data without missing required sections. | Pending manual execution | Not Run | High | Manual Functional | DishServiceTests.GetByIdAsync_ReturnsMatchingDish; NutritionServiceTests.GetByDishIdAsync_ReturnsNutrition | Manual check should use real UI data.
TC-DISH-003 | Dish Menu | Controllers/DishController.cs | Handle missing dish details | Application is running. | Open details URL with an id that does not exist. | Dish id 999999 | Application returns NotFound or a controlled error response. | Pending manual execution | Not Run | Medium | Negative Manual | DishControllerTests.Details_ReturnsNotFoundWhenNull | Confirms negative route behavior in browser.
TC-DISH-004 | Dish Management | Controllers/DishController.cs | Create a dish | User has access to dish creation page; categories exist. | Open Dish Create; enter required fields; optionally upload image; save. | Dish QA Pasta; category existing; price valid; description test data | Dish is created and user is redirected to the dish list. | Pending manual execution | Not Run | High | Manual Functional | DishControllerTests.Create_Post_Valid_RedirectsToIndex_AndCreatesDish; DishServiceTests.CreateAsync_AddsDishToDatabase | Controller has Create GET and POST actions.
TC-DISH-005 | Dish Management | Controllers/DishController.cs | Edit an existing dish | A test dish exists and user has access to edit page. | Open Dish Edit for test dish; change description or category; save. | Dish QA Pasta updated description | Dish changes are saved and visible on details/list page. | Pending manual execution | Not Run | High | Manual Functional | Partial service coverage through DishServiceTests | DishController includes Edit GET and POST actions.
TC-DISH-006 | Dish Management | Controllers/DishController.cs | Delete an existing dish | A removable test dish exists. | Open Delete for the test dish; confirm deletion. | Dish QA Pasta | Dish is removed and does not appear in the dish list. | Pending manual execution | Not Run | Medium | Manual Functional | DishControllerTests.DeleteConfirmed_CallsDeleteAndRedirects; DishServiceTests.DeleteAsync_RemovesDishFromDatabase | Use a test-only record.
TC-CAT-001 | Categories | Controllers/CategoryController.cs | Create category | User has access to category management. | Open Category Create; enter a category name; save. | Category QA Lunch | Category is created and appears in category list or can be assigned to dishes. | Pending manual execution | Not Run | Medium | Manual Functional | CategoryServiceTests.CreateAsync_AddsCategory | Controller supports Create GET and POST.
TC-CAT-002 | Categories | Controllers/CategoryController.cs | Edit category | A test category exists. | Open Category Edit; change category name; save. | Category QA Lunch Updated | Category is updated without duplicate or validation error. | Pending manual execution | Not Run | Medium | Manual Functional | CategoryServiceTests.UpdateAsync_ChangesCategory | Confirm UI and service behavior align.
TC-CAT-003 | Categories | Controllers/CategoryController.cs | Delete category | A test category exists and is safe to remove. | Open Category Delete; confirm deletion. | Category QA Lunch Updated | Category is removed and no broken dish links are visible. | Pending manual execution | Not Run | Medium | Manual Functional | CategoryServiceTests.DeleteAsync_RemovesCategory | Use a category not linked to important demo dishes.
TC-ALL-001 | Allergens | Controllers/AllergenController.cs | Create allergen | User has access to allergen management. | Open Allergen Create; enter allergen name and icon URL if required; save. | Allergen QA Sesame; icon /test/icon.png | Allergen is created and can be linked to dishes. | Pending manual execution | Not Run | Medium | Manual Functional | AllergenServiceTests.CreateAsync_AddsAllergen | Allergen model includes AllergenName and IconUrl.
TC-ALL-002 | Allergens | Controllers/AllergenController.cs | Edit allergen | A test allergen exists. | Open Allergen Edit; change allergen name or icon URL; save. | Allergen QA Sesame Updated | Allergen changes are saved. | Pending manual execution | Not Run | Medium | Manual Functional | AllergenServiceTests.UpdateAsync_ChangesAllergen | Confirm linked dish display remains stable.
TC-ALL-003 | Allergens | Controllers/AllergenController.cs | Delete allergen | A test allergen exists and is safe to remove. | Open Allergen Delete; confirm deletion. | Allergen QA Sesame Updated | Allergen is removed from list and no linked display breaks. | Pending manual execution | Not Run | Medium | Manual Functional | AllergenServiceTests.DeleteAsync_RemovesAllergen | Use test-only allergen data.
TC-ING-001 | Ingredients | Services/IngredientService.cs | Create ingredient through management or dish workflow | User has access to ingredient-related workflow. | Create or select an ingredient from the UI path used by the app. | Ingredient QA Tomato | Ingredient is stored and can be linked to dishes. | Pending manual execution | Not Run | Medium | Manual Functional | IngredientServiceTests.CreateAsync_AddsIngredient; IngredientServiceTests.FindOrCreateByNameAsync_FindsExistingOrCreates | No IngredientController was found; verify through available UI flow.
TC-ING-002 | Ingredients | Services/IngredientService.cs | Display dishes by ingredient | At least one dish is linked to a test ingredient. | Open or verify the UI path that displays dishes for an ingredient. | Ingredient QA Tomato linked to dish | Linked dishes are returned and displayed correctly. | Pending manual execution | Not Run | Low | Manual Functional | IngredientServiceTests.GetDishesByIngredientAsync_ReturnsLinkedDishes | Manual route depends on available UI.
TC-NUT-001 | Nutrition | Controllers/NutritionController.cs | Create or edit nutrition values | A dish exists. | Open Nutrition Edit for a dish; enter nutrition fields; save. | Calories 500; protein 20; carbs 60; fat 15 | Nutrition record is saved and visible on dish details. | Pending manual execution | Not Run | Medium | Manual Functional | NutritionServiceTests.CreateAsync_AddsNutrition; NutritionServiceTests.UpdateAsync_ChangesNutrition | Controller exposes Edit GET and POST.
TC-NUT-002 | Nutrition | Controllers/NutritionController.cs | Delete nutrition values | A dish has nutrition values. | Use Nutrition Delete action for the dish. | Existing dish id with nutrition | Nutrition values are removed and dish details remain stable. | Pending manual execution | Not Run | Medium | Manual Functional | NutritionServiceTests.DeleteByDishIdAsync_RemovesNutrition | Controller exposes Delete POST.
TC-CART-001 | Cart | Controllers/CartController.cs; Views/Cart/Index.cshtml | Display user cart | User is logged in. | Open /Cart/Index. | Authenticated user id | Cart page displays current user's cart items or empty state. | Pending manual execution | Not Run | High | Manual Functional | CartControllerTests.Index_ReturnsViewWithCart; CartServiceTests.GetUserCartAsync_ReturnsItemsOrderedByTargetDate | Also verify behavior when cart is empty.
TC-CART-002 | Cart | Controllers/CartController.cs | Add dish to cart | User is logged in; at least one dish exists. | From dish/menu UI, submit Add with dishId, quantity, and targetDate. | Dish id existing; quantity 2; target date tomorrow | Item is added to the cart and user is redirected to cart index. | Pending manual execution | Not Run | High | Manual Functional | CartControllerTests.Add_Post_RedirectsToIndex_AndCallsAdd; CartServiceTests.AddToCartAsync_InsertsNewCartItem_WhenNoExistingItem | CartController Add is an HTTP POST action.
TC-CART-003 | Cart | Services/CartService.cs | Increment same dish and same target date | User already has the same dish for the same target date in cart. | Add the same dish with the same target date again. | Same dish id; same target date; quantity 1 | Existing cart item quantity increases instead of creating an incorrect duplicate. | Pending manual execution | Not Run | Medium | Manual Functional | CartServiceTests.AddToCartAsync_IncrementsQuantity_WhenExistingItemHasSameDate | Check displayed quantity in cart UI.
TC-CART-004 | Cart | Controllers/CartController.cs | Update cart item quantity and note | User has an item in cart. | Change quantity and note through cart UI; submit update. | Quantity 3; note No onions | Service updates quantity and note; controller returns OK; UI reflects changes. | Pending manual execution | Not Run | High | Manual Functional | CartControllerTests.Update_Post_ReturnsOk_AndCallsUpdate; CartServiceTests.UpdateItemAsync_UpdatesQuantityAndNote_WhenItemExists | Update action is HTTP POST.
TC-CART-005 | Cart | Controllers/CartController.cs | Remove single cart item | User has at least one item in cart. | Click or submit Remove for one cart item. | Existing cart item id | Selected item is removed and the user is redirected to cart index. | Pending manual execution | Not Run | High | Manual Functional | CartControllerTests.Remove_Post_RedirectsToIndex_AndCallsRemove; CartServiceTests.RemoveItemAsync_RemovesItem_WhenItemExists | Confirm other items remain.
TC-CART-006 | Cart | Controllers/CartController.cs | Clear cart | User has multiple cart items. | Use Clear cart action. | Authenticated user with cart items | All items for the user are removed from cart. | Pending manual execution | Not Run | Medium | Manual Functional | CartControllerTests.Clear_Post_RedirectsToIndex_AndCallsClear; CartServiceTests.ClearCartAsync_RemovesAllUserItems | Confirm page shows empty state.
TC-RES-001 | Reservation | Controllers/ReservationController.cs; Views/Reservation/Checkout.cshtml | Open checkout | User is logged in and cart contains items. | Open /Reservation/Checkout. | Authenticated user with cart item | Checkout page displays cart items prepared for reservation. | Pending manual execution | Not Run | High | Manual Functional | ReservationControllerTests.Checkout_ReturnsViewWithCart | Checkout reads user cart.
TC-RES-002 | Reservation | Controllers/ReservationController.cs | Reject reservation with no selected items | Checkout page is available. | Submit CreateReservation without selected item ids. | SelectedItemIds empty; target date tomorrow | User is redirected to checkout with an error message. | Pending manual execution | Not Run | High | Negative Manual | ReservationControllerTests.CreateReservation_Post_NoItemsSelected_RedirectsToCheckout; ReservationServiceTests.CreateReservationAsync_ThrowsWhenNoItemsSelected | Backend rule exists; verify UI feedback.
TC-RES-003 | Reservation | Controllers/ReservationController.cs | Reject reservation before tomorrow | Checkout has at least one selected item. | Submit CreateReservation with target date today or in the past. | Selected item id existing; target date today | User is redirected to checkout with invalid date error. | Pending manual execution | Not Run | High | Negative Manual | ReservationControllerTests.CreateReservation_Post_TargetDateBeforeTomorrow_RedirectsToCheckout; ReservationServiceTests.CreateReservationAsync_ThrowsWhenTargetDateBeforeTomorrow | Controller minimum date is DateTime.Today.AddDays(1).
TC-RES-004 | Reservation | Controllers/ReservationController.cs; Views/Reservation/Success.cshtml | Create valid reservation | User is logged in and has selected cart items. | Submit CreateReservation with selected item ids and a target date tomorrow or later. | Selected item id existing; target date tomorrow | Reservation is created and user is redirected to Success page. | Pending manual execution | Not Run | High | Manual Functional | ReservationControllerTests.CreateReservation_Post_Valid_RedirectsToSuccess; ReservationServiceTests.CreateReservationAsync_CreatesOrderAndCallsRemoveItems | Success page should display reservation details.
TC-RES-005 | Reservation | Controllers/ReservationController.cs | Open success page for existing reservation | A reservation exists. | Open /Reservation/Success with an existing reservation id. | Existing reservation id | Success view displays reservation data. | Pending manual execution | Not Run | Medium | Manual Functional | ReservationControllerTests.Success_ReturnsViewWhenFound; ReservationServiceTests.GetByIdAsync_ReturnsOrderWithDetails | Check order details are present.
TC-RES-006 | Reservation | Controllers/ReservationController.cs | Handle success page for missing reservation | Application is running. | Open /Reservation/Success with a non-existing id. | Reservation id 999999 | Application returns NotFound or a controlled error response. | Pending manual execution | Not Run | Medium | Negative Manual | ReservationControllerTests.Success_ReturnsNotFoundWhenNull | Confirms negative path.
TC-RES-007 | Reservation Manager | Controllers/ReservationController.cs | Manager lookup with invalid code | Manager lookup page is accessible. | Open ManagerLookup; submit a reservation code that does not exist. | Code BADCODE | Page shows no reservation found message. | Pending manual execution | Not Run | Medium | Negative Manual | ReservationControllerTests.ManagerLookup_Post_NoReservation_ShowsError | Access control should also be checked.
TC-RES-008 | Reservation Manager | Controllers/ReservationController.cs | Update reservation status | A reservation exists and user has intended manager/kitchen access. | Submit UpdateStatus with reservation id and new status. | Reservation id existing; status Ready | Reservation status is updated and user is redirected to ManagerLookup. | Pending manual execution | Not Run | High | Manual Functional | ReservationControllerTests.UpdateStatus_Post_RedirectsToManagerLookup; ReservationServiceTests.UpdateStatusAsync_ChangesOrderStatus | Verify only intended roles can do this.
TC-ORD-001 | Orders | Controllers/OrdersController.cs; Views/Orders/MyOrders.cshtml | View current user's orders | User is logged in with role User and has at least one reservation/order. | Open /Orders/MyOrders. | Authenticated User role | Only the current user's orders are displayed. | Pending manual execution | Not Run | High | Manual Functional | No dedicated automated coverage | OrdersController has Authorize(Roles = User).
TC-ORD-002 | Orders | Controllers/OrdersController.cs | View user order statistics | User is logged in with role User. | Open /Orders/Stats. | Authenticated User role | User statistics are displayed and match known order data. | Pending manual execution | Not Run | Medium | Manual Functional | No dedicated automated coverage | Stats action calls IOrderService.GetUserStatsAsync.
TC-POLL-001 | Polls | Controllers/PollController.cs | Display active polls | At least one active poll exists. | Open Poll Index page. | Existing active poll | Active polls are listed. | Pending manual execution | Not Run | Medium | Manual Functional | PollServiceTests.GetActivePollsAsync_ReturnsOnlyActive | PollController exposes Index action.
TC-POLL-002 | Polls | Controllers/PollController.cs | Create poll with options | User has access to poll creation. | Open Poll Create; enter question and multiple options; save. | Question What meal next week; options Pasta, Soup | Poll and options are created. | Pending manual execution | Not Run | Medium | Manual Functional | PollServiceTests.CreatePollAsync_AddsPollAndOptions | Create POST uses anti-forgery token.
TC-POLL-003 | Polls | Controllers/PollController.cs | Vote in poll | Active poll exists and user has not voted. | Open poll details; choose option; submit vote. | Existing poll id and option id | Vote is saved and user is redirected or shown updated state. | Pending manual execution | Not Run | Medium | Manual Functional | VoteServiceTests.AddVoteAsync_AddsVote; PollServiceTests.HasUserVotedAsync_ReturnsTrueWhenVoted | Check duplicate vote behavior manually.
TC-POLL-004 | Polls | Controllers/PollController.cs | Display poll results | A poll exists with at least one vote. | Open Poll Results for the poll. | Existing poll id with votes | Options and vote counts are displayed correctly. | Pending manual execution | Not Run | Low | Manual Functional | PollServiceTests.GetOptionsAsync_ReturnsOptionsWithVotes; VoteServiceTests.GetVotesForPollAsync_ReturnsVotes | Validate displayed totals.
TC-POLL-005 | Polls | Controllers/PollController.cs | Delete poll | A test poll exists and is safe to remove. | Submit Delete for test poll. | Test poll id | Poll is deleted and related options/votes do not remain visible. | Pending manual execution | Not Run | Medium | Manual Functional | PollServiceTests.DeletePollAsync_RemovesPollAndCascade | Use test-only poll.
TC-SEC-001 | Security | Controllers/*.cs; Program.cs | Verify unauthorized access handling | User is logged out. | Attempt direct GET and POST access to Cart, Reservation, Poll, Dish, Category, Allergen, and Nutrition actions. | Logged-out browser session; direct URLs and form posts | User is blocked, redirected, or receives a controlled authorization response where appropriate. | Pending manual execution | Not Run | High | Security Manual | No direct automated coverage | Risk Register highlights missing visible Authorize attributes on several controllers.
TC-UI-001 | UI | Views/**/*.cshtml; wwwroot/css/*.css | Desktop layout smoke check | Application is running with representative data. | Open Home, Dish list, Dish details, Cart, Checkout, Success, My Orders, Admin, and Kitchen pages at desktop size. | Desktop browser width 1366 px | Text, buttons, tables, and navigation are visible and usable. | Pending manual execution | Not Run | Medium | Manual UI | No automated browser coverage | xUnit tests do not render Razor views in a browser.
TC-UI-002 | UI | Views/**/*.cshtml; wwwroot/css/*.css | Mobile layout smoke check | Application is running with representative data. | Open Home, Dish list, Dish details, Cart, Checkout, and My Orders at mobile width. | Mobile browser width 390 px | No overlapping text, clipped controls, or unusable navigation. | Pending manual execution | Not Run | Medium | Manual UI | No automated browser coverage | Focus on final presentation reliability.

## Automated Coverage
Test File | Test Count | Module | Covered Behaviors | Framework | Data Store or Test Double | Latest Known Result | Coverage Gaps | Source Artifact
AllergenServiceTests.cs | 5 | Allergens | Get all allergens; create allergen; update allergen; delete allergen; return dishes linked to allergen. | xUnit | EF Core InMemory | Automated Passed | Controller UI and authorization are manual only. | CanteenReservationSystem.Tests/AllergenServiceTests.cs
CartControllerTests.cs | 5 | Cart Controller | Index view; Add POST redirect and service call; Update POST OK; Remove POST redirect; Clear POST redirect. | xUnit | Fake cart service | Automated Passed | Browser UI, authentication, and direct unauthorized access are manual only. | CanteenReservationSystem.Tests/CartControllerTests.cs
CartServiceTests.cs | 6 | Cart Service | Insert new item; increment same item and date; order by target date; update quantity and note; remove item; clear user cart. | xUnit | EF Core InMemory | Automated Passed | Real database and Razor page rendering are not covered. | CanteenReservationSystem.Tests/CartServiceTests.cs
CategoryServiceTests.cs | 5 | Categories | Get all categories; create category; update category; delete category; return dishes linked to category. | xUnit | EF Core InMemory | Automated Passed | Category controller UI and role access are manual only. | CanteenReservationSystem.Tests/CategoryServiceTests.cs
DishControllerTests.cs | 5 | Dish Controller | Index view; Create GET; valid Create POST; Details NotFound; DeleteConfirmed redirect and service call. | xUnit | Fake services and in-memory user store | Automated Passed | Edit flow, image upload, and browser rendering are manual only. | CanteenReservationSystem.Tests/DishControllerTests.cs
DishServiceTests.cs | 5 | Dish Service | Get all dishes; get matching dish by id; create dish; delete dish; filter by category. | xUnit | EF Core InMemory | Automated Passed | Full menu UI behavior and image handling are not covered. | CanteenReservationSystem.Tests/DishServiceTests.cs
IngredientServiceTests.cs | 6 | Ingredients | Get all ingredients; create ingredient; update ingredient; delete ingredient; return dishes by ingredient; find or create by name. | xUnit | EF Core InMemory | Automated Passed | No IngredientController was found; available UI path must be checked manually. | CanteenReservationSystem.Tests/IngredientServiceTests.cs
NutritionServiceTests.cs | 4 | Nutrition | Get nutrition by dish id; create nutrition; update nutrition; delete nutrition by dish id. | xUnit | EF Core InMemory | Automated Passed | Nutrition edit/delete UI needs manual browser verification. | CanteenReservationSystem.Tests/NutritionServiceTests.cs
PollServiceTests.cs | 5 | Polls | Return active polls; create poll with options; detect user vote; get options with votes; delete poll cascade. | xUnit | EF Core InMemory | Automated Passed | Poll controller access and duplicate vote UI behavior are manual only. | CanteenReservationSystem.Tests/PollServiceTests.cs
ReservationControllerTests.cs | 8 | Reservation Controller | Checkout; no selected items redirect; invalid date redirect; valid reservation success redirect; success found; success not found; manager lookup error; update status redirect. | xUnit | Fake cart and reservation services | Automated Passed | Browser checkout flow and manager role access are manual only. | CanteenReservationSystem.Tests/ReservationControllerTests.cs
ReservationServiceTests.cs | 5 | Reservation Service | Throw on no selected items; throw on target date before tomorrow; create order and remove items; get order with details; update order status. | xUnit | EF Core InMemory and fake cart service | Automated Passed | Real database and full UI journey are not covered. | CanteenReservationSystem.Tests/ReservationServiceTests.cs
VoteServiceTests.cs | 3 | Votes | Return false when user has not voted; add vote; return votes for poll. | xUnit | EF Core InMemory | Automated Passed | Duplicate vote prevention through UI is manual only. | CanteenReservationSystem.Tests/VoteServiceTests.cs
UnitTest1.cs | 1 | Placeholder | Default placeholder test exists. | xUnit | No project data dependency | Automated Passed | Does not provide meaningful project coverage. | CanteenReservationSystem.Tests/UnitTest1.cs

## Execution Checklist
Run Item ID | Activity | Command or Navigation | Expected Outcome | Latest Status | Owner | Evidence | Notes
EXEC-001 | Restore packages | dotnet restore CanteenReservationSystem.sln --verbosity minimal | NuGet packages restore successfully. | Passed | QA | Restore completed successfully on 2026-05-28. | Low severity package warnings were recorded in the risk register.
EXEC-002 | Build web application | dotnet build CanteenReservationSystem/CanteenReservationSystem.csproj --no-restore --verbosity minimal | Web application compiles with zero errors. | Passed | QA | Build succeeded on 2026-05-28. | Warnings are tracked separately; no build errors remained.
EXEC-003 | Run automated tests | dotnet test CanteenReservationSystem.Tests/CanteenReservationSystem.Tests.csproj --no-restore --verbosity minimal | All xUnit tests pass. | Passed | QA | Passed 63; Failed 0; Skipped 0. | Automated baseline is green.
EXEC-004 | Prepare manual data | Create or identify user, dish, category, allergen, ingredient, poll, cart item, and reservation records. | Manual test data is available. | Pending | QA | Manual execution not started in this workbook. | Use test-only records where deletion is required.
EXEC-005 | Execute manual functional tests | Run every row in Manual Test Cases sheet from TC-AUTH-001 through TC-POLL-005. | Each row has Passed, Failed, or Blocked status after execution. | Not Run | QA | Manual results are pending. | Fill Actual Result and Status during testing.
EXEC-006 | Execute security checks | Run TC-SEC-001 using logged-out and wrong-role browser sessions. | Access is blocked or controlled according to expected role behavior. | Not Run | QA | Manual results are pending. | Use the risk register to prioritize this check.
EXEC-007 | Execute responsive checks | Run TC-UI-001 and TC-UI-002 on desktop and mobile widths. | No layout overlap or unusable controls. | Not Run | QA | Manual results are pending. | Record screenshots if a defect is found.
EXEC-008 | Report failed tests | For every Failed manual test, create a bug report in the next QA workbook. | Every failed test links to a bug id. | Pending | QA | Bug register will be added in a later commit if requested. | Use clear steps, expected result, and actual result.