## Risk Register
Risk ID | Area | Source Artifact | Project Evidence | Risk Description | Cause or Trigger | Impact | Likelihood | Severity | Priority | Existing Control | Recommended QA Action | Owner | Status | Date Identified | Target Date | Related Files
RISK-001 | Authorization and access control | Controller attributes review | Only OrdersController contains [Authorize(Roles = "User")]; CartController, ReservationController, PollController, DishController, CategoryController, AllergenController, and NutritionController have no visible [Authorize] attribute. | User-specific or admin-like actions may be reachable without the correct role if no other route-level protection exists. | Direct URL or POST request to controller actions by a logged-out user or a user with the wrong role. | Unauthorized access to cart, reservation, manager lookup, poll, or admin data. | Medium | High | High | ASP.NET authentication and authorization middleware is enabled in Program.cs; OrdersController has role protection. | Manually verify logged-out and wrong-role access for Cart, Reservation, Poll, Dish, Category, Allergen, and Nutrition routes before release. | Backend developer and QA | Open | 2026-05-28 | Before final review | CanteenReservationSystem/Controllers/*.cs; CanteenReservationSystem/Program.cs
RISK-002 | Null user identity handling | Build warning review and controller code | CartController and ReservationController call User.FindFirstValue(ClaimTypes.NameIdentifier); build warnings include possible null reference arguments for userId. | Controller actions may pass null userId into services when the request is not authenticated. | Logged-out request reaches a user-specific action. | Runtime exceptions, incorrect data association, or failed reservation/cart operations. | Medium | High | High | Some service and controller unit tests pass; OrdersController is role-protected. | Validate behavior for logged-out users and require authentication before user-specific service calls. | Backend developer and QA | Open | 2026-05-28 | Before manual QA sign-off | CartController.cs; ReservationController.cs; OrdersController.cs
RISK-003 | Manager reservation workflow | ReservationController review | ManagerLookup, ManagerLookup POST, and UpdateStatus actions are present in ReservationController without a visible role attribute. | Reservation status management may not be restricted to kitchen or manager roles. | A normal user or logged-out user attempts to search by reservation code or update status. | Reservation data exposure or incorrect order status changes. | Medium | High | High | ReservationControllerTests cover manager lookup and status update logic. | Verify role-based access for manager lookup and status update; add role checks if manual testing confirms open access. | Backend developer and QA | Open | 2026-05-28 | Before final review | CanteenReservationSystem/Controllers/ReservationController.cs
RISK-004 | Database configuration | appsettings and project files | appsettings.json uses SQL Server connection string Server=.;Database=CanteenDB; project folder also contains canteen.db, canteen.db-shm, and canteen.db-wal SQLite files. | Development environments may use different database engines or stale database files. | Running the app on a machine without local SQL Server or with a different expected database. | Application startup or data validation may fail even when unit tests pass. | Medium | Medium | Medium | EF Core configuration is explicit in Program.cs with UseSqlServer; unit tests use EF Core InMemory. | Confirm the official development database setup and document required SQL Server or migration steps. | Database owner and QA | Review | 2026-05-28 | Before demo setup | CanteenReservationSystem/appsettings.json; CanteenReservationSystem/Program.cs; canteen.db*
RISK-005 | Package security | dotnet restore/build/test output | NuGet warnings report low severity vulnerability for NuGet.Packaging 6.12.1 and NuGet.Protocol 6.12.1. | Transitive package version includes a known advisory. | Dependency audit is reviewed during release preparation. | Low security exposure or reviewer concern if dependency warnings are left unexplained. | Low | Low | Medium | Medium | The automated test suite passes and the warning is low severity. | Record the warning and update affected packages if the team can do so without breaking .NET 10 package compatibility. | Backend developer | Review | 2026-05-28 | Before final submission | CanteenReservationSystem.csproj; CanteenReservationSystem.Tests.csproj; restore output
RISK-006 | Automated coverage gap | Test project file inventory | The test project has 63 xUnit tests for services and selected controllers; there are no browser or end-to-end tests in the repository. | Unit tests do not execute real Razor views, browser navigation, layout behavior, or full login flow. | UI, routing, or integrated workflow changes are introduced after unit tests pass. | Visual or workflow defects may remain until manual testing. | High | Medium | High | High | xUnit service/controller coverage exists for Cart, Dish, Reservation, Category, Allergen, Ingredient, Nutrition, Poll, and Vote modules. | Plan manual browser testing for authentication, menu, cart, checkout, manager lookup, and responsive layouts. | QA | Open | 2026-05-28 | Before QA sign-off | CanteenReservationSystem.Tests/*.cs; CanteenReservationSystem/Views/**/*.cshtml
RISK-007 | Authentication flow coverage | Areas/Identity files and test inventory | Identity pages for Login, Logout, and Register exist under Areas/Identity, but no custom xUnit test file targets Identity UI behavior. | Authentication UI is scaffolded and handled by ASP.NET Identity, while project-specific tests focus on services and selected controllers. | Login, register, validation, or logout behavior differs from team expectations. | User onboarding or access testing may fail during demo. | Medium | Medium | Medium | Medium | ASP.NET Identity is configured with AddDefaultIdentity and RequireConfirmedAccount=false. | Manually test register, valid login, invalid login, logout, and role-based navigation. | QA and backend developer | Open | 2026-05-28 | Before manual QA sign-off | Areas/Identity/Pages/Account/*.cshtml; Program.cs
RISK-008 | Input validation and reservation rules | ReservationController and ReservationService tests | Reservation logic rejects empty item selection and target dates before tomorrow; these rules are covered by ReservationControllerTests and ReservationServiceTests. | Rules are implemented in controller/service code, but the user interface still needs real browser verification. | User submits checkout form with no selected items or an invalid target date. | User may see unclear feedback or bypass client-side expectations even if backend rejects the request. | Medium | Medium | Medium | Medium | Automated tests passed for empty selection and invalid target date scenarios. | Manually verify error messages, redirect behavior, and date controls on the Checkout page. | QA | Open | 2026-05-28 | Before final review | ReservationController.cs; ReservationServiceTests.cs; ReservationControllerTests.cs; Views/Reservation/Checkout.cshtml
RISK-009 | Placeholder test quality | Automated test inventory | UnitTest1.cs contains one default-style placeholder test in addition to the real service and controller tests. | A placeholder test can inflate the total test count without adding meaningful coverage. | Reviewers inspect the test suite or require proof of useful automated testing. | QA credibility may be reduced if placeholder tests are presented as functional coverage. | High | Low | Medium | Medium | There are 62 other meaningful tests across service and controller test files. | Replace UnitTest1.cs with a real test or exclude it from coverage claims in the QA summary. | QA and backend developer | Review | 2026-05-28 | Before final submission | CanteenReservationSystem.Tests/UnitTest1.cs
RISK-010 | Order service coverage | Controller and test inventory | OrdersController has MyOrders and Stats actions with [Authorize(Roles = "User")], but there is no dedicated OrderServiceTests.cs file in the test project. | Order retrieval and user statistics may rely on service logic that is not directly covered by the listed tests. | Order history or stats are changed or used in final demo. | Incorrect order data or statistics may be missed by automated tests. | Medium | Medium | Medium | Medium | OrdersController uses role-based authorization; reservation tests cover order creation indirectly. | Manually verify My Orders and Stats for a user with known reservations; consider adding OrderService unit tests later. | QA and backend developer | Open | 2026-05-28 | Before final review | CanteenReservationSystem/Controllers/OrdersController.cs; CanteenReservationSystem.Tests/*.cs
RISK-011 | Razor view and responsive layout | Views and wwwroot assets | Views exist for Cart, Dish, Orders, Reservation, Home Admin, Home Kitchen, and Shared layout; CSS and JS assets exist under wwwroot. | Razor views and static assets are not validated by the xUnit service tests. | Page is opened on mobile or desktop with real data. | Broken layout, hidden buttons, or missing visual content may appear during presentation. | Medium | Medium | Medium | Medium | Static assets and views are present in the repository. | Perform manual responsive checks on Menu, Dish Details, Cart, Checkout, Success, My Orders, Admin, and Kitchen pages. | QA and frontend developer | Open | 2026-05-28 | Before presentation | CanteenReservationSystem/Views/**/*.cshtml; CanteenReservationSystem/wwwroot/css/*.css; CanteenReservationSystem/wwwroot/js/*.js
RISK-012 | Build environment stability | Observed build/test execution | The web app project builds successfully and dotnet test passes 63 tests, but the full solution build previously hit OneDrive obj file access issues until commands were run with proper permissions. | The project is stored in a OneDrive path where generated obj/bin files can be locked or permission-restricted. | Another team member runs build/test from the same synced directory. | False build failures may slow QA or confuse final verification. | Medium | Medium | Medium | Medium | After restore and proper permissions, web app build succeeded and all tests passed. | Run restore/build/test sequentially and avoid parallel dotnet commands in the same solution; move workspace out of synced storage if issues repeat. | QA and all developers | Review | 2026-05-28 | Before final verification | OneDrive workspace path; CanteenReservationSystem/obj; CanteenReservationSystem.Tests/obj

## Project Evidence
Evidence ID | Project Source | Observed Fact | QA Interpretation | Status
EVID-001 | dotnet test CanteenReservationSystem.Tests.csproj --no-restore | Passed: 63, Failed: 0, Skipped: 0, Duration: 18 seconds. | Automated unit/controller test baseline is currently green. | Passed
EVID-002 | CanteenReservationSystem.Tests folder | 13 C# test files were found, including service tests and selected controller tests. | Automated coverage exists but is not full browser coverage. | Review
EVID-003 | CanteenReservationSystem.Tests.csproj | Uses xUnit, Microsoft.NET.Test.Sdk, coverlet.collector, and Microsoft.EntityFrameworkCore.InMemory. | The test suite is built for unit/controller testing with an in-memory database. | Review
EVID-004 | CanteenReservationSystem/Program.cs | The application uses AddDefaultIdentity, UseAuthentication, UseAuthorization, and UseSqlServer. | Authentication middleware is present, but controller attributes still need route-level review. | Review
EVID-005 | Controllers attribute scan | OrdersController has [Authorize(Roles = "User")]; other scanned controllers do not show visible [Authorize] attributes. | Access control must be manually verified for user-specific and admin-like actions. | Open
EVID-006 | CanteenReservationSystem/appsettings.json | DefaultConnection points to SQL Server database CanteenDB on Server=.; local SQLite database files also exist. | Database setup should be clarified for repeatable QA execution. | Review
EVID-007 | dotnet restore/build/test output | Low severity NuGet vulnerability warnings were reported for NuGet.Packaging and NuGet.Protocol 6.12.1. | Dependency warning is not test-blocking but should be tracked. | Review
EVID-008 | CanteenReservationSystem/Views and wwwroot | Razor views and CSS/JS files exist for user-facing pages. | Manual UI and responsive testing are required because xUnit does not render the browser UI. | Open

## Risk Matrix
Field | Allowed Value | Meaning | How QA Uses It
Likelihood | Low | The issue is possible but unlikely based on current project evidence. | Track and retest if related code changes.
Likelihood | Medium | The issue can reasonably happen in normal development or manual testing. | Include it in the manual QA checklist.
Likelihood | High | The issue is likely because evidence already points to a gap or repeated warning. | Treat it as a priority QA focus.
Severity | Low | Minor quality issue with low user or demo impact. | Document and review when time allows.
Severity | Medium | Could affect a feature, reviewer confidence, or repeatable setup. | Verify before final submission.
Severity | High | Could affect access control, core workflows, or the final demo. | Verify and resolve before QA sign-off.
Status | Open | The risk is active and still needs QA or development action. | Keep visible in the register.
Status | Review | The risk is not blocking but needs team decision or documentation. | Review before final submission.
Status | Controlled | The risk has an existing mitigation and only needs regression monitoring. | Retest if related code changes.